MMIW Task Force Timeline

JANUARY

- Creating a data gathering plan in consultation with Gabe and TF

- Identify stakeholders, develop involvement plan, and conduct outreach via email

- Design IPRA Requests in consultation with Gabe and TF

FEBRUARY

- Follow-up and confirm key stakeholders

- Submit IPRA Requests

- Design surveys and community hearings in consultation with Gabe and TF

- Develop the framework for gathering MMIW cases

MARCH

- Convene key stakeholders for feedback on data gathering plan

- Test and conduct one round of survey gathering

- Begin promotion/outreach for community hearings

APRIL

- Conduct community hearings

- Begin mapping MMIW cases

- Draft literature review of reports and research on MMIW

- Second round of survey gathering

MAY

- Wrap-up community hearings

- Evaluate and analyze data (surveys, IPRA requests, and community hearings)

- Develop recommendations

JUNE

- DRAFT OF FINAL REPORT